Jijiya: AI-Powered Maternal and Neonatal Risk Stratification Tool for Antenatal Care in Nigerian Primary Health Facilities

Introduction

JIJIYA is a point-of-care maternal and neonatal risk stratification tool designed to support antenatal care delivery across primary health facilities in Nigeria. The name is drawn from the Hausa word for midwife. Nigeria records approximately 1,047 maternal deaths per 100,000 live births, accounting for roughly 20% of global maternal mortality — a rate more than 14 times the SDG 3.1 target of fewer than 70 per 100,000. Sub-Saharan Africa bore 70% of all global maternal deaths in 2023, and the region is projected to miss the 2030 target by a factor of seven at the current trajectory. Hypertensive disorders, haemorrhage, and sepsis drive over 60% of these deaths, most of which are preventable through timely identification during routine ANC contacts.

Primary health care holds great potential to improve maternal, newborn, and child health (MNCH) outcomes. Yet risk stratification at this level remains informal, clinician-dependent, and unsupported by any validated decision-support system. Health workers collect rich ANC data — blood pressure, haemoglobin, gestational age, weight gain, obstetric history — but have no systematic mechanism for converting it into a standardised risk classification they can act on immediately. JIJIYA is designed to fill that gap. It processes structured ANC inputs and returns a three-tier risk classification — Low, Moderate, or High — with clinical justifications and recommended interventions, within seconds, at the point of care. It does not replace the midwife. It equips her.

Problem Statement:

Nigeria has no integrated, validated national tool for standardising antenatal risk stratification across its PHC network. High-risk pregnancies go unidentified at the facilities where the earliest contact with the health system occurs. Referrals are delayed until complications become emergencies. Existing WHO ANC risk scoring frameworks are technically sound but require clinical training and cognitive bandwidth that overburdened staff frequently cannot sustain across a full clinic day. Paper-based checklists exist in some facilities but are inconsistently applied and entirely disconnected from any feedback mechanism

Project Objectives:

The central goal of JIJIYA is to deploy a validated, AI-powered decision-support tool that standardises antenatal risk stratification across Nigerian PHC facilities and generates structured clinical intelligence that health authorities can act on at facility, state, and national levels. Specific objectives are:

- Deploy a point-of-care risk stratification interface operable without specialist training, returning a three-tier classification within ten seconds of ANC data submission.

- Achieve sensitivity greater than 85% and specificity greater than 88% for High-risk classification against midwife reference assessment across eight PHC facilities in Abuja's FCT.

- Implement an optional bioacoustic module using Google's HeAR foundation model to detect fetal heart sound distress patterns beyond structured clinical inputs.

- Establish offline-capable deployment for PHC facilities with intermittent connectivity, using a locally deployed quantised model variant.

- Deliver a programme dashboard for district health offices providing facility-level risk distribution, referral tracking, and trend analysis integrated with DHIS2.

Target performance indicators: sensitivity above 85%; specificity above 88%; Cohen's kappa above 0.70; response time under ten seconds; offline uptime above 95%; health worker usability score above 4.0 out of 5.0.

Methodology and Approach

JIJIYA operates through four integrated components grounded in clinical decision-support theory and WHO task-shifting frameworks for maternal health in LMICs.

## Structured ANC Data Intake

Health workers enter ANC visit data through a browser-based structured form accessible on any Android tablet or smartphone. The form captures blood pressure, haemoglobin, gestational age, weight gain trajectory, gravidity, parity, and presenting symptoms. Field validation and inline reference ranges minimise entry errors. Data entry takes under three minutes per visit.

## Generative Risk Classification

ANC data is submitted to MedGemma 27B, Google's open-weight medical LLM fine-tuned on clinical notes, EHR data, and structured health records. The model performs generative classification — reasoning through clinical inputs and returning a structured JSON output constrained to a validated schema. Each output includes the risk tier, clinical flags driving the assessment, recommended intervention, and a confidence note flagging ambiguous or incomplete data. Uncertain cases are routed to human expert review. The model surfaces clinical intelligence. The health worker acts on it.

## Optional Bioacoustic Module

Recorded fetal heart sounds are processed through Google's HeAR foundation model, producing 512-dimensional embeddings. A lightweight linear probe classifier fine-tuned on labelled fetal heart recordings generates a distress risk signal. JIJIYA is fully functional without this module; it is treated as an enhancement layer.

## Programme Dashboard

Individual classifications aggregate in real time into a dashboard for district health officers and state MNCH programme managers, providing facility-level risk distribution, referral outcomes, multi-visit trend tracking, and geographic heat maps. RESTful API endpoints support DHIS2 integration

Technical Stack

MedGemma 27B and quantised MedGemma 4B (Google HAI-DEF, open-weight) for risk classification; HeAR (Google HAI-DEF) for bioacoustic embedding; FastAPI with Python 3.11; PostgreSQL for production storage; SQLite for offline facility-level storage; Streamlit for the health worker interface and dashboard; Docker and Docker Compose; Hugging Face Transformers 4.40 and PyTorch 2.x; llama.cpp or Ollama for quantised offline model serving; ReportLab for PDF export; Pydantic v2 for JSON schema enforcement; Librosa and SoundFile for audio preprocessing; and a Progressive Web App service worker for offline browser caching. Deployment via Google Vertex AI, Hugging Face Inference API, or Render. Offline facilities use a quantised MedGemma 4B variant in GGUF format deployable on a standard laptop without GPU.

Implementation Timeline

| Phase | Key Activities | Period |
| --- | --- | --- |
| Phase 1 | FastAPI setup, MedGemma 27B integration, ANC schema design, prompt engineering, output validation. | Weeks 1–2 |
| Phase 2 | Risk scoring refinement, Streamlit interface, offline SQLite integration, PWA configuration. | Weeks 3–4 |
| Phase 3 | Referral PDF export, programme dashboard, HeAR audio pipeline, linear probe classifier. | Weeks 5–6 |
| Phase 4 | Prospective validation across 8 FCT PHC facilities (n=340). Sensitivity, specificity, kappa evaluation. | Weeks 7–12 |
| Phase 5 | Summit demo, user training materials, DHIS2 integration, documentation, state deployment planning. | Weeks 13–16 |

Governance, Data Privacy and Ethics

JIJIYA is implemented under the AI Team's technical leadership with clinical governance from a designated medical advisory group. Core partners are NPHCDA, FCT Health and Human Services Secretariat, WHO Nigeria, UNICEF Nigeria, and the Nigerian Medical Association. All partner roles are formalised through signed MoUs before validation activities commence. A joint oversight committee convenes monthly throughout development and validation.

Risk and Mitigation

| Risk | Mitigation |
| --- | --- |
| False negative High-risk classification | Sensitivity-prioritised prompt tuning; mandatory clinical flags for out-of-range BP and Hb readings; post-validation LoRA fine-tuning on local ANC records |
| Offline quantised model underperformance | Benchmark 4B vs 27B on ANC test set before offline deployment; rule-based triage fallback for critical flags when offline |
| Insufficient fetal heart sound data for HeAR fine-tuning | Bioacoustic module optional at launch; data collection incorporated as secondary objective in validation study |
| Low PHC staff digital literacy | Minimal-friction UI design; facilitator training in deployment plan; Hausa and Yoruba language options in post-MVP roadmap |
| Patient data privacy breach | Local-first processing; end-to-end encryption; no PII to external APIs; independent governance audit provisions |

Expected Outcomes and Impact

Direct deliverables include a validated AI-powered risk stratification tool meeting stated sensitivity, specificity, and concordance targets; a peer-reviewed validation study submitted to the AI4PH Research and Implementation Symposium; an operational programme dashboard for MNCH monitoring; a replicable validation framework for open-weight LLM deployment in maternal health across LMICs; and complete technical documentation and user training materials for PHC staff.

Resources Required

Human resources: AI and ML Engineer, lead developer, full-time for sixteen weeks; clinical advisor, part-time four to six hours per week; maternal health specialist on consultancy basis for Weeks 1 through 4; UX reviewer ad hoc across two review cycles; data protection officer ad hoc for Weeks 1 through 2. Infrastructure: GPU-capable cloud environment via Vertex AI or Render for MedGemma 27B inference; local llama.cpp deployment for offline facilities; Docker containerisation; and facility-level Android devices for the validation study. Funding is required for personnel costs, cloud infrastructure, validation study logistics across eight FCT facilities, device procurement, ethical review board fees, and monitoring activities.

Conclusion

Nigeria's maternal mortality challenge cannot be addressed through improvements to service delivery alone. The risk identification infrastructure at the point where most pregnant women engage the health system has not kept pace with the clinical data those contacts generate. JIJIYA brings together a pre-validated AI classification pipeline, an implementation approach grounded in PHC operational realities, and a governance structure built on existing maternal health programme infrastructure. The path from this concept to a working national tool is defined and achievable within the proposed timeline. Our organisation invites NPHCDA, state health authorities, development partners, and funding bodies to support full implementation. The objective is straightforward: to ensure that no high-risk pregnancy in Nigeria goes unidentified because the health worker conducting the antenatal visit lacked the tool to recognise it.